## Sheet1
Cure University
Signup
| Front End |  | 2.5 hours | 2.5
|  | Attractive UI RnD |  | 0
|  | Html |  | 0
|  | CSS |  | 0
|  | Bootstrap |  | 0
| Jquery |  | 0.5 hours | 0.5
|  | Validation checks |  | 0
| Code Behind |  | 1.5 hours | 1.5
|  | BAL |  | 0
|  | DLL |  | 0 |  |  |  | Planned for today
| Database |  | 0.75 hours | 0.75 |  |  |  | Done
|  | SP Insert in users table |  | 0
|  | SP Insert in messages table |  | 0
0
Login |  |  |  | 0
| Front End |  | 1.5 hours | 1.5
|  | Html |  | 0
|  | CSS |  | 0
|  | Bootstrap |  | 0
| Jquery |  | 0.5 hours | 0.5
|  | Validation checks |  | 0
| Code Behind |  | 01 hour | 1
|  | BAL |  | 0
|  | DLL |  | 0
| Database |  | 0.5 hours | 0.5
|  | SP verify user from table |  | 0
0
Student page |  |  |  | 0
| Course Registration |  |  | 0
|  | Front End | 3 hours | 3
|  | Data Table |  | 0
0
|  | Jquery | 0.5 hours | 0.5
|  | Credit hour count check |  | 0
0
|  | Code Behind | 1 hour | 1
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 0.5 hours | 1
|  | SP Registercourse |  | 0
0
| Choose Teacher |  |  | 0
|  | Front End | 1.5 hour | 1.5
|  | Data Table |  | 0
0
|  | Jquery | 0.5 hours | 1 | 16.75
|  | Storing option |  | 0
0
|  | Code Behind | 1 hour | 1
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 1 hour | 1
|  | SP ViewTeachers |  | 0
|  | SP assign teacher |  | 0
0
| Update Profile |  |  | 0
|  | Front End | 1 hour | 1
0
|  | Jquery | 0.5 hours | 1
|  | Validation checks |  | 0
0
|  | Code Behind | 0.5hours | 0.75
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 0.5 hours | 0.5
|  | SP Updateprofile |  | 0
0
| Take Quiz |  |  | 0
|  | Front End | 0.25 hours | 0.75
|  | a Simple html page |  | 0
0
| Submit assignment |  |  | 0
|  | Front end |  | 0.5 | 22.75 | Extra Effort uploading files | Is a bug always chooses Calculus
0
0
| View Message |  |  | 0
|  | Front End | 0.5 hours | 0.5
|  | implementation of a message box |  | 0
0
|  | Code Behind | 0.5 hours | 0.5
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Databse | 0.25 hours | 0.25
|  | SP view message |  | 0 | 24.5
0
Teacher Page |  |  |  | 0
| Update Profile |  |  | 0
|  | Front End | 0.1 hours | 1
0
|  | Jquery | 0.5 hours | 1
|  | Validation checks |  | 0
0
|  | Code Behind | 0.5 hours | 0.5
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 0.25 hours | 0.25
|  | SP Updateprofile |  | 0
0
| Edit Course |  |  | 0
|  | Front End | 2 hours | 2
|  | Drop down lists |  | 0
0
|  | Jquery | 0.5 hours | 1
|  | Storing option |  | 0
0
|  | Code Behind | 0.5 hours | 0.75
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 0.5 hours | 0.75
|  | SP update course |  | 0
0
| View Message |  |  | 0
|  | Front End | 0.5 hours | 0.5
|  | implementation of a message box |  | 0
0
|  | Code Behind | 0.5 hours | 1
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Databse | 0.25 hours | 0.75
|  | SP view message |  | 0
0
| Send Message |  |  | 0
|  | Front End | 0.5 hours | 0.5
|  | implementation of a message box |  | 0
0
|  | Code Behind | 0.5 hours | 0.5
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Databse | 0.25 hours | 0.25
|  | SP send message |  | 0
0
| Upload Assessment Score |  |  | 0
|  | Front End | 2 hours | 2
|  | implementation of data table |  | 0
0
|  | Code Behind | 0.5 hours | 0.5
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Databse | 0.5 hours | 0.5
|  | SP update assesssmetn score |  | 0
0
0
0
0
Admin. Page |  |  |  | 0
| View All Teachers |  |  | 0
|  | Front End |  | 0
|  | Use of Data Table | 2 hour | 2
0
|  | Code Behind | 0.5 hours | 0.5
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 0.5 hours | 0.5
|  | SP View all Teachers |  | 0
0
| View All Students |  |  | 0
|  | Front End |  | 0
|  | Use of Data Table | 1 hour | 1
0
|  | Code Behind | 0.5 hours | 0.75
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 0.25 hours | 0.5
|  | SP View all Students |  | 0
0
| Block/Suspend Entity |  |  | 0
|  | front end | 0.25 hours | 0.25
|  | Code Behind | 0.5 hours | 0.5
|  | BAL |  | 0
|  | DLL |  | 0
0
|  | Database | 1 hour | 1
|  | SP Mark teacher blocked/suspended |  | 0
|  | SP Mark student blocked/suspended |  | 0
0
Miscellenous tasks |  |  | 3 hours | 3
Model Making |  |  | 2 hours | 2
Table making |  |  | 2 hours | 2
Daily Code Review |  |  | 3 hours | 3
TOTAL TIME |  |  | 42.25 hours | 55.25